## SUBSCRIBER
USER ACCEPTANCE TEST (UAT) - FOR USSD
USSD NUMBER: *347*75985# - SandBox Environment
USSD NUMBER: *347*215# - Live
Script Execution: 3rd March, 2021
Audience | Category | Test Case | Type | Description | Expected Result | Actual Result | Pass / Fail | Comments
| NEW SUBSCRIBER | New Subscriber / Subscriber Dials *347*75985# | 1 | MSISDN linked to a Client | Display New Subscriber Menu | New Subscriber Menu was displayed | Pass | Format email being sent properly, include additionall information --> screenshot. will be sent
| NEW USSD SESSION | New USSD Session / Merchant Dial 08644039000 | 1 | Msisdn linked to a merchant | Display Main menu |  | Pass
| NEW USSD SESSION | New USSD Session / Agent Dial 08644039000 | 1 | Msisdn linked to an agent | Display Main menu |  | Pass
| MERCHANT SETTINGS | Change language | 1 | Merchant : Dial 08644039000, 3, valid code, valid language option | Change merchant's language |  | Pass
| NEW USSD SESSION | New USSD Session / Subscriber Dials *347*75985# | 1 | MSISDN linked to a Client | Display Subscriber Main Menu | Subscriber Main Menu was displayed | Pass
| SUBSCRIBER BALANCE | Subscriber Selects Option 1 | 1 | Subscriber dials *347*75985#, 1 | Display Subscriber's Balance | Correct subscriber's balance was displayed | Pass
| NEXT PAGE | Subscriber Selects Option 8 | 1 | Subscriber dials *347*75985#, 8 | Display Subscriber Next Page | Subscriber was able to view the next page on the menu | Pass
| WALLET TRANSFER | 2348059090616 Completes Option 2: Correct PIN | 1 | Subscriber dials *347*75985#, 2, 100, 1, 2348059090613, 1, 1234 | Display Wallet Transfer Success | Wallet transfer was successful | Pass
| WALLET TRANSFER | 2348059090616 Completes Option 2: Wrong PIN | 1 | Subscriber dials *347*75985#, 2, 100, 1, 2348059090613, 1, 1444 | Display Wallet Transfer Failure | Wallet transfer was unsuccessful, and the correct response was displayed | Pass
| WALLET TRANSFER | 2348059090616 Completes Option 2: Unknown Subscriber | 1 | Subscriber dials *347*75985#, 2, 100, 1, 2348059000000, 1, 1444 | Display Wallet Transfer Failure | Wallet transfer was unsuccessful, and the correct response was displayed | Pass
| BANK TRANSFER | 2348059090616 Completes Option 3: Correct PIN & Account | 1 | Subscriber dials *347*75985#, 3, 1, 1, 0085444675, 1, 1234 | Display Bank Transfer Success | Bank transfer was successful | Pass
| BANK TRANSFER | 2348059090616 Completes Option 3: Wrong Account | 1 | Subscriber dials*347*75985#, 3, 1, 1, 123, 1, 1234 | Display Bank Account Validation Failed Response | Bank transfer was unsuccessful, and the correct response was displayed | Pass | Consider differentiating responses when an actual invalid account has been entered and when the system can't validate an account
| BANK TRANSFER | 2348059090616 Completes Option 3: Wrong PIN | 1 | Subscriber dials*347*75985#, 3, 1, 1, 0085444675, 1, 0000 | Display Bank Transfer Failure Response | Bank transfer was unsuccessful, and the correct response was displayed | Pass
| BILL PAYMENTS | 2348059090616 Selects Option 4 | 1 | Subscriber dials *347*75985#, 4, | Display Bill Payments Flow | Bill Payments Flow was displayed | Pass | Pending Implementation
| CASHOUT | 2348059090616 Selects Option 5 | 1 | Subscriber dials*347*75985#, 5, | ATM Cashout Flow | ATM Cashout Flow was displayed | Pass | Pending Implementation
| BUY AIRTIME | 2348059090616 Selects Option 6 | 1 | Subscriber dials*347*75985#, 6, 1, | Buy Airtime Flow | Buy Airtime Flow was displayed | Pass | Pending Implementation
| CHANGE PIN | 2348059090616 Completes Option 7: Correct Current PIN & No PIN Mismatch | 1 | Subscriber dials*347*75985#, 6, 7, 1234, 0000, 0000 | Display Change PIN Success | User's PIN was changed successfully | Pass
| CHANGE PIN | 2348059090616 Completes Option 7: Wrong Current PIN | 1 | Subscriber dials *347*75985#, 6, 7, 1444, 0000, 0000 | Display Wrong PIN Response | PIN change was unsuccessful, and the correct response was displayed | Pass
| CHANGE PIN | 2348059090616 Completes Option 7: Pin Mismatch | 1 | Subscriber dials*347*75985#, 6, 7, 1234, 0100, 0000 | Display PIN Mismatch Response | PIN change was unsuccessful, and the correct response was displayed | Pass
| FUND MY AKU | 2348059090616 Selects Option 9 | 1 | Subscriber dials *347*75985#, 8, 9 | Display Fund AKU Wallet Screen | Fund AKU Wallet Screen was displayed | Pass | Pending Implementation
| MY AKU | 2348059090616 Selects Option 10 | 1 | Subscriber dials *347*75985#, 8, 10 | Display My Aku Menu | User's detail {firstname, lastname, email address, phone number & balance} was displayed | Pass

## AGENT
USER ACCEPTANCE TEST (UAT) - FOR USSD
USSD NUMBER: *347*75985*101# - SandBox Environment
USSD NUMBER: *347*215*101# - Live
Script Execution: 3rd March, 2021
Audience | Category | Test Case | Type | Description | Expected Result | Actual Result | Pass / Fail | Comments
| NEW USSD SESSION | New USSD Session / Client Dial 08644039000 | 1 | Msisdn linked to a client | Display Main menu
| NEW USSD SESSION | New USSD Session / Agent Dial 08644039000 | 1 | Msisdn linked to an agent | Display Main menu
| CLIENT PIN | Client Send Option 1 | 1 | Option 1 gives acess to client's menu | Display client's main menu
| AGENT CODE | Agent Send Option 2 | 1 | Option 2 gives acess to Agent menu | Display Agent's main menu
| NEW USSD SESSION | New Agent Session / Agent Dials *347*75985*101# | 1 | MSISDN linked to a client | Display Agent Main Menu | Agent Main Menu was displayed | Pass
| CHECK BALANCE | Agent Selects Option 1 | 1 | Agent Dials *347*75985*101#, 1 | Display Agent Balance and Commission | Agent Balance and Commission was displayed | Pass
| WALLET TRANSFER | 2348059090611 Completes Optiont 2 | 1 | Agent Dials *347*75985*101#, 2, 100, 1, 2348059090648, 1, 1234 | Display Agent Wallet Transfer Success | Transfer didn't go through. Subscriber didn't receive money | Pass | Correct typo --> change message to "Transfer Successful": Transfer Successful! Transfers currently work for only Agent to Agent: For agent to subscriber we have it as cashin and cashout.
| WALLET TRANSFER | 2348059090611 Completes Optiont 2: Wrong Pin | 1 | Agent Dials *347*75985*101#, 2, 100, 1, 2348059090648, 1, 1444 | Display Agent Wallet Transfer Failure - Incorrect PIN Entered | Transfer didn't go through. and correct response was displayed | Pass
| WALLET TRANSFER | 2348059090611 Completes Option 2: Unknown Agent | 1 | Agent Dials *347*75985*101#, 2, 100, 1, 2348059090000, 1, 1444 | Display Agent Wallet Transfer Failure - Agent Does Not Exist | Transfer didn't go through. and correct response was displayed | Pass
| BANK TRANSFER | 2348059090611 Completes Option 3: Correct PIN & Account | 1 | Agent Dials *347*75985*101#, 3, 1, 1, 0085444675, 1, 1234 | Display Bank Transfer Success | Transfer didn't go through, a wrong response was displayed | Pass
| BANK TRANSFER | 2348059090611 Completes Option 3: Wrong Account | 1 | Agent Dials *347*75985*101#, 3, 1, 1, 123, 1, 1234 | Display Bank Account Validation Failed Response | Transfer didn't go through, and correct response was displayed | Pass
| BANK TRANSFER | 2348059090611 Completes Option 3: Wrong PIN | 1 | Agent Dials *347*75985*101#, 3, 1, 1, 0085444675, 1, 0000 | Display Bank Transfer Failure Response | Transfer didn't go through, and correct response was displayed | Pass
| CASHOUT | 2348059090611 Completes Option 4: Correct PIN & Account | 1 | Agent Dials *347*75985*101#, 4, 100, 2347065912538, 1, 3083, 1234 | Display Cashout Success Response | Cashout was completed successfully, and correct response was displayed | Pass
| CASHOUT | 2348059090611 Completes Option 4: Incorrect Agent PIN | 1 | Agent Dials *347*75985*101#, 4, 100, 2347065912538, 1, 3083, 0000 | Display Cashout Failure Response - Incorrect Agent Code Entered | Cashout didn't go through, and correct response wasn't displayed | Fail | Wrong Response Displayed: Unique error code required
| CASHOUT | 2348059090611 Completes Option 4: Incorrect Subscriber PIN | 1 | Agent Dials *347*75985*101#, 4, 100, 2347065912538, 1, 0000, 1234 | Display Cashout Failure Response - Incorrect Subscriber PIN Entered | Cashout didn't go through, and the correct response was displayed | Pass
| CASHOUT | 2348059090611 Completes Option 4: Unknown Subscriber | 1 | Agent Dials *347*75985*101#, 4, 100, 2347000000000, 1, 3083, 1234 | Display Cashout Failure Response - Subscriber isn't Registered | Cashout didn't go through, and the correct response was displayed | Pass
| CASHIN | 2348059090611 Completes Option 5: Correct PIN & Account | 1 | Agent Dials *347*75985*101#, 5, 100, 2348059090616, 1, 1234 | Display Cashin Success Response | Cashin was completed successfully, and correct response was displayed | Pass
| CASHIN | 2348059090611 Completes Option 5: Incorrect Agent PIN | 1 | Agent Dials *347*75985*101#, 5, 100, 2347065912538, 1, 0000 | Display Cashin Failure Response - Incorrect Agent Code Entered | Cashin didn't go through, and the correct response was displayed | Pass
| CASHIN | 2348059090611 Completes Option 5: Unknown Subscriber | 1 | Agent Dials *347*75985*101#, 5, 100, 2347000000000, 1, 1234 | Display Cashin Failure Response - Subscriber isn't Registered | Cashin didn't go through, and the correct response was displayed | Pass
| AIRTIME | 2348059090611 Selects Option 6 | 1 | Agent Dials *347*75985*101#, 2, 6 | Display Airtime Menu Flow | Airtime Menu Flow was displayed | Pass | Pending Implementation
| AGENT INFORMATIONS | Agent Informations | 1 | Agent : Dial 08644039000, 5, valid code | Display agent's informations
| CLIENT ACCOUNTS MANAGEMENT | Block client account | 1 | Agent : Dial 08644039000, 4, 1, registered client nb, valid code | Blocks the client
| CLIENT ACCOUNTS MANAGEMENT | Block client account | 1 | Blocked client was using the USSD service | Shutdowns the client's USSD session